## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone1: Project Prep
Align and evaluate stakeholders |  |  |  | 5
Research menu tablets | Seydou provides sme support |  |  | 3
Create project charter | estimate based on historical project |  |  | 4
Schedule kickoff meeting |  |  |  | 1
Generate quotes and review costs |  |  |  | 5
Calculate projections |  |  |  | 1
Sign contract with a vendor |  |  |  | 5
Vendor timeline and deliverables schedule |  |  |  | 5
Milestone2: Hardware Installation and Budget
Order tablets/tablet shipping |  |  |  | 10
Hire an electrician to install the wires | Both GMs have the respect of their staffs |  |  | 5
Communicate tablet benefits of the tablet GM as champion |  |  |  | 1
Install tablets in North and Downtown locations |  |  |  | 4
Set up Menu for tablets | Carter may be doing a revamp, could add to time |  |  | 12
Build and decide on daily/weekly promotions (mockups) | coordinate with Gilli and Alex, Deanna and Carter |  |  | 8
Integrate tablets with existing systems (POS) | Seydou provides sme support |  |  | 3
Make short guide next to each tablet for guests | QC |  |  | 2
Milestone3: Go live
Inhouse training on the tablets to train the staff | Gm lead and kitchen management execution |  |  | 2
Upgrade the restaurant's security system |  |  |  | 4
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  |  |  | 1
Milestone4: Beta testing and debugging
Test tablets with a mock service friends and family | Need to confirm with Carter |  |  | 0.5
Create launch day plan | refine training and tech support |  |  | 1
Create messaging about payment portal security to display on the tablets | Confirm software |  |  | 7
Milestone5: Project Monitoring
Schedule customer feedback resources for the rollout | tablet surveys |  |  | 5
Schedule swap of old tablets with new ones for month 2 after launch date | shipping delays |  |  | 60

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Align and evaluate stakeholders |  | 5 | 1 | 5 | 10 | H
Research menu tablets | Seydou provides sme support | 3 | 2 | 3 | 5 | H
Schedule kickoff meeting | Milestone1: Project Prep |  |  |  |  | H
Generate quotes and review costs |  | 7 | 5 | 7 | 14 | H
Calculate projections |  | 1 | 0.5 | 1 | 4 | H
Sign contract with a vendor |  | 5 | 2 | 5 | 10 | M
Vendor timeline and deliverables schedule |  | 7 | 4 | 7 | 14 | M
Hire an electrician to install the wires | Milestone2: Hardware Installation and Budget | 5 | 3 | 5 | 7 | H
Communicate tablet benefits of the tablet GM as champion | Both GMs have the respect of their staffs | 1 | 1 | 1 | 1 | H
Install tablets in North and Downtown locations |  | 14 | 10 | 14 | 21 | L
Inhouse training on the tablets to train the staff | Milestone3: Go live | 2 | 1 | 2 | 10 | M
Upgrade the restaurant's security system |  | 1 | 1 | 1 | 7 | H
Create a procedure for securing tablets at the end of the night (at the table or in a safe) |  | 1 | 0.5 | 1 | 3 | H
Test tablets with a mock service friends and family | Milestone4: Beta testing and debuggin | 0.5 | 0.2 | 0.5 | 2 | M
Create launch day plan | Need to confirm with Carter | 1 | 0.5 | 1 | 5 | M
Create messaging about payment portal security to display on the tablets |  | 7 | 4 | 7 | 14 | M
Schedule customer feedback resources for the rollout | Milestone5: Project Monitoring | 5 | 2 | 5 | 14 | M

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
10 Best Restaurant POS Systems | https://tech.co/pos-system/best-restaurant-pos-systems | 2022-03-03 | excellent guide to compare various systems
POS market size | https://www.marketwatch.com/press-release/restaurant-pos-software-market-size-2022-by-manufactures-share-types-applications-regions-recent-trends-with-covid-19-impact-analysis-and-forecast-to-2028-2022-03-07 | 2022-03-03 | align with experience and data points for analysis
Rollout a new POS to your restaurant chain | https://www.speedlinesolutions.com/blog/rollout-a-new-pos-to-your-restaurant-chain | 2022-03-03

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
FALSE
Customer Satisfaction | Are we providing the custlemres | Are customers having a better dining experience with the tablets? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait time | FALSE
Have we improved customer satisfaction?
Tablet Use | Are the tablets easy to use | Do all the tablets work as expected? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | FALSE
|  | Are the tablets functioning properly? | Waitstaff can log into their tablet accounts on the first try | FALSE
|  | How quickly are customers learning how to navigate the tablets? | Appetizer sales increase by 10%
Order accuracy | the amount of time between placing an order and delivering it to the table | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order | FALSE
Checkout Time |  |  |  | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Customer Satisfaction | Are customers having a better dining experience with the tablets? | Guests with shorter wait times report wanting to return 20% more often than those with longer wait time | have you visited S&S before? | Yes/No | Yes | No
| Have we improved customer satisfaction? |  | What was your experience with the tablets? | Open-ended | Open-ended
Tablet Use | Do all the tablets work as expected? | Guests who use the tablets are 50% more likely to recommend the restaurant to a friend | Has your wait time improved and by how much? | Scaled
| Are the tablets functioning properly? | Waitstaff can log into their tablet accounts on the first try | On a scale of 1-5 with 1 not accurate and 5 total accuracy how accuratne was your order? | Multiple choice | 1- Total accurate | 2- Nearly accurate | 3- Accurate | 4 - Not accuarate | 5 - competlely inaccuatate
| How quickly are customers learning how to navigate the tablets? | Appetizer sales increase by 10% | Was there a particular feature of the tablet that you enjoy? | Open-ended | Open-ended
Order accuracy | Are customers receiving the correct orders? | 98% of customers who use tablets receive the correct order | Would you recommend S&S to friend? | Yes/No
Checkout Time |  |  | Was your checkout time 5 minutes or less, 5-10 minutes, or greater than 10? | Multiple choice | 1- <5 | 5 to 10 | >10
|  |  | Was there anything the tablet that was difficult? | Open-ended | Open-ended
|  |  | Was your dining experience better than your previous better | Yes/No | Yes | No
|  |  | The tablet improved my overall dining experience | True/False | TRUE | FALSE
|  |  | What was your overall satisfaction | Scaled | 1 - Completely satisfied | 2 - Very satisfied | 3 - Satisfied | 4 - Somewhat dissatisfied | 5 - dissatisfied