## Slide 1: Survey Evaluation Analysis

## Slide 2
Summary Tablet Test Launch
The team successfully launched the table tablets at the two pilot locations (North and Downtown)
This was the result of the planning and coordination to:
  Find vendors
  Achieve deliverables
  Forecast correct timelines and anticipate possible setbacks
Proper installation, software, training and testing

## Slide 3
Overview
We wanted to measure the effectiveness of this milestone through Quality Measures:
Tablet use: Are the tablets easy to use and function as was planned for and expected?
  Are the tablets working properly?
  How quickly do the customers navigate through the tablet?
  Is the functionality correct?
  Indicators:
    Guests who use the tablets are 50% more likely to recommend the restaurant to a friend
    Waitstaff can log into their tablet accounts on the first try
    Appetizer sales increase by 10%

## Slide 4
Findings
The survey results provided excellent analysis:
82% of respondents found the checkout easy to use
  Though a majority it falls below our target of 95%

## Slide 5
Next Steps
The tablets overall were successful as far as overall functionality but there needs to be some revision for training software and ease of use of design.

## Slide 6
Next Steps
We need to refine the tablets for a more seamless interface and amend our contract for a more intuitive software interface.