## Tasks and Timeline
Sauce & Spoon Project Plan
Task | Notes | Start Date | Due Date | Duration | Task Owner | Status | PHASE ONE | [14 empty] | PHASE TWO | [14 empty] | PHASE THREE | [14 empty] | PHASE FOUR
[7 empty] | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
Milestone: Project Initiation - gathering all data
Schedule kickoff meeting |  |  |  | 1
Create project charter | estimate based on historical project |  |  | 4
Schedule project Charter meeting |  |  |  | 1
Adjust project charter according to details |  |  |  | 1
Establish criteria for tablet vendors / what type of product | align with stakeholders for long-term goals, adjusted from historical project |  |  | 4.6667
Get quotes and choose vendor | from info known and historical stuff |  |  | 4.6667
Milestone: Plan for Tablets Rollout
Order tablets/tablet shipping | info from alignment with Seydou, update: shipping delay (see email) - older tablets will be rolled out first |  |  | 10
Set up Menu for tablets | get help from Gilli and Alex, consult with Carter - Carter may be doing a revamp, could add to time) |  |  | 11.6667
Build and decide on daily/weekly promotions (mockups) | coordinate with Gilli and Alex, Deanna as well, depends on Carter |  |  | 8
Connect with marketing team of S&S to get branding set up for tablets | designers are on standby |  |  | 2
Implement branding & new menu in new tablet menus | separate vendor; must contact and get quote; check budget change, get go-ahead from stakeholders if over budget |  |  | 2
Establish measurement criteria for goals - process, reports | we already have all the info here, need to get final signoff on it |  |  | 1
Get final approval from main stakeholders | 1 day buffer for tweaks, based on previous project |  |  | 2
Upload new menues/weekly promotions on tablets | 3-4h if all goes well, depends on marketing team and Carter can become a regular activity |  |  | 1
Milestone: Staff adoption and training of tablets
Set up meeting with wait staff and GMs to discuss effect of tablets rollout | include effect of tablets on tips |  |  | 2
Set up training of key staff members by external team |  |  |  | 3
Set up training plan/materials for Kitchen |  |  |  | 3
Set up training plan/materials for Staff |  |  |  | 3
Training for staff in each separate location | may take more if not everyone is available, and extra sessions need to be scheduled |  |  | 4
Milestone: Installing Tablets in Restaurants
Schedule integration/installation days | coordinate with Gilly and Alex, resti closed or 2 half days. Only scheduling |  |  | 1
Install tablets at tables | coordinate with Seydou to also set up an electrician and coordinate with electrician, resti closed. Schedule two half days. Added a buffer if things go wrong 1 day/location |  |  | 4
Integrate tablets with existing systems (POS) | get specialized support here? (as part of vendor package?) |  |  | 3
Make short guide next to each tablet for guests | review, etc |  |  | 2
Introduce Service day with family to staff and get buy in |  |  |  | 2
Organise a service day with family and friends to test out new tablets
Schedule swap of old tablets with new ones for month 2 after launch date | info from new conversation with Seydou - shipping delays

## Task Brainstorm
Task Brainstorm
Task | Notes | Estimated Duration (Days) | Optimistic | Most Likely | Pessimistic | Confidence Rating (H/M/L) | Known Dates
Milestone: Project Initiation - gathering all data
Schedule kickoff meeting |  | 1
Create project charter | estimate based on historical project | 4 | 1 | 4 | 5 | H
Schedule project Charter meeting |  | 1
Adjust project charter according to details |  | 1
Establish criteria for tablet vendors / what type of product | align with stakeholders for long-term goals, adjusted from historical project | 4.6667 | 3 | 4 | 7 | H
Get quotes and choose vendor | from info known and historical stuff | 4.6667 | 2 | 5 | 7 | H
Milestone: Plan for Tablets Rollout
Order tablets/tablet shipping | info from alignment with Seydou, update: shipping delay (see email) - older tablets will be rolled out first | 10 | 7 | 10 | 13 | H
Set up Menu for tablets | get help from Gilli and Alex, consult with Carter - Carter may be doing a revamp, could add to time) | 11.6667 | 10 | 11 | 14 | M
Build and decide on daily/weekly promotions (mockups) | coordinate with Gilli and Alex, Deanna as well, depends on Carter | 8 | 3 | 7 | 14 | M
Connect with marketing team of S&S to get branding set up for tablets | designers are on standby | 2
Implement branding & new menu in new tablet menus | separate vendor; must contact and get quote; check budget change, get go-ahead from stakeholders if over budget | 2 | 1 | 2 | 3 | M
Establish measurement criteria for goals - process, reports | we already have all the info here, need to get final signoff on it | 1 |  |  |  | H
Get final approval from main stakeholders | 1 day buffer for tweaks, based on previous project | 2 | 1 | 2 | 2 | H
Upload new menues/weekly promotions on tablets | 3-4h if all goes well, depends on marketing team and Carter can become a regular activity | 1 | 1 | 1 | 1 | L
Milestone: Staff adoption and training of tablets
Set up meeting with wait staff and GMs to discuss effect of tablets rollout | include effect of tablets on tips | 2 | 2 | 2 | 2
Set up training of key staff members by external team |  | 3 | 3 | 3 | 3 | H
Set up training plan/materials for Kitchen |  | 3 | 3 | 3 | 3 | H
Set up training plan/materials for Staff |  | 3 | 3 | 3 | 3 | H
Training for staff in each separate location | may take more if not everyone is available, and extra sessions need to be scheduled | 4 | 2 | 2 | 4 | M
Milestone: Installing Tablets in Restaurants
Schedule integration/installation days | coordinate with Gilly and Alex, resti closed or 2 half days. Only scheduling | 1 |  |  |  | H
Install tablets at tables | coordinate with Seydou to also set up an electrician and coordinate with electrician, resti closed. Schedule two half days. Added a buffer if things go wrong 1 day/location | 4 | 2 | 4 | 6 | M
Integrate tablets with existing systems (POS) | get specialized support here? (as part of vendor package?) | 3 | 1 | 3 | 5 | L
Make short guide next to each tablet for guests | review, etc | 2 | 1 | 3 | 7
Introduce Service day with family to staff and get buy in |  | 2
Organise a service day with family and friends to test out new tablets
Schedule swap of old tablets with new ones for month 2 after launch date | info from new conversation with Seydou - shipping delays

## Additional Resources
Additional Resources
Title | Link | Date Added | Notes
7 vital steps in successful tech rollout | https://www.qsrautomations.com/blog/restaurant-technology/7-vital-steps-technology-rollout/ | 5.03.2022 | check solutions with all stakeholders, to see which one is clearer and better for them, but keep in mind project prios
Restaurant rebood: use cases for tablet table tops rollouts | https://www.pmi.org/learning/library/restaurant-reboot-9754 | 5.03.2022 | appetizer sales spiked 20% for 1 restaurant, deserts spiked another 20% for another, but there could be resistance from staff when adopting the new tech, because of the view that tech takes away from the service experience
Rollout a new POS to your restaurant chain | https://www.speedlinesolutions.com/blog/rollout-a-new-pos-to-your-restaurant-chain | 5.03.2022 | The most successful chains align corporate growth goals with tactics and technology They involve every department that either uses the POS, or is impacted by the data it collects They run the implementation in a disciplined manner They follow up with the key stakeholders throughout and after the project

## Quality and Evaluation
Quality and Evaluation
Quality Standards | Quality Standards
Category | Criteria/Description | Evaluation Questions | Evaluation Indicators | Criteria Met?
Customer Satisfaction | Faster, mor effective experience | "Has the waiting time between placing an order and getting the mean decreased? Do guests spend less time in the restaurant? Do guests spend less time waiting before being seated? | - average ticket time is eight minutes for appetizers and 12-15 minutes for entrees - bringing down the average table turn time by 30 minutes - less than 10 mins waiting time before getting seated | FALSE
Customer Satisfaction | Have order delivered correctly |  | - 98% order accuracy | FALSE
Customer Satisfaction | Checkout process is seamless and easy to navigate from a user perspective. |  | - average one-minute checkout time - less than 5% of customers who use the tablets to report technical issues each week. | FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE
FALSE

## Survey Questions
Survey Questions
Quality Standards |  |  |  |  | Question Answer Options (depends on question type)
Criteria/Description | Evaluation Questions | Evaluation Indicators state the specific type of data you need to collect to answer your evaluation questions | Survey Question | Question Type | Option #1 | Option #2 | Option #3 | Option #4 | Option #5
Faster, mor effective experience | Has the waiting time between placing an order and getting the mean decreased? | - average ticket time is eight minutes for appetizers and 12-15 minutes for entrees | 1. How long would you say you waited from placing your order to receiving your meal? | Scaled
Faster, more effective experience | Has the waiting time between placing an order and getting the mean decreased? | - average ticket time is eight minutes for appetizers and 12-15 minutes for entrees | 2. How would you rate your waiting time between ordering and receiving your meal?
Faster, more effective experience | Do guests spend less time in the restaurant? | - bringing down the average table turn time by 30 minutes | 1. How long would you say you spend in our restaurant on average per visit? | Scaled | Less than 30 mins | 30-60 mins | 60-90 mins | over 90 mins
Faster, more effective experience | Do guests spend less time waiting before being seated? | - less than 10 mins waiting time before getting seated | 1. How long would you say you waited before being seated? | Scaled | No wait | Less than 5 mins | Less than 10 mins | Less than 30 mins | 30 mins or more
Have order delivered correctly | How many orders are being returned? (waiter view) | - 98% order accuracy | 1. How many orders would you say you get returned on an average shift? | Scaled | 0 | 1 | 2 | 3 | more than 3
Have order delivered correctly | Are there any incorrect orders coming from the kitchen? (customer view) | - 98% order accuracy | 1. If you've had to return an order to the kitchen, could you please describe what the issue was? | Open-ended | - | - | - | - | -
Checkout process is seamless and easy to navigate from a user perspective. | How quickly are the guests able to check out? | - average one-minute checkout time | 1. On a scale of 1-5 (1=lowest, 5=highest) how intuitive do you find the tablet for use in ordering and checking out? | Scaled | 1 | 2 | 3 | 4 | 5
Checkout process is seamless and easy to navigate from a user perspective. | What is the frequency of assistance requests? | - less than 5% of customers who use the tablets to report technical issues each week. | 1. Do you ever receive requests for help from customers for the checkout process? | Yes/No | Yes | No
Checkout process is seamless and easy to navigate from a user perspective. | What is the nature of issues for the checkout process? (waiter view) | - less than 5% of customers who use the tablets to report technical issues each week. | 2. If yes to the previous, what would be the most common indicated issues? | Open-ended | - | - | - | - | -
Checkout process is seamless and easy to navigate from a user perspective. | How often do issues get reported? (waiter view) | - less than 5% of customers who use the tablets to report technical issues each week. | 3. How often do you receive requests for help from customers for the checkout process | Scaled | 0 issues | 1-2 issues per shift | 3-5 issues per shift | 5-7 issues per shift | more than 7 issues per shift
Checkout process is seamless and easy to navigate from a user perspective. | How often do issues get reported? (customer view) | - less than 5% of customers who use the tablets to report technical issues each week. | 1. Have you encountered any issues while navigating the tablet? | Yes/No | Yes | No
Checkout process is seamless and easy to navigate from a user perspective. | How often do issues get reported? (customer view) | - less than 5% of customers who use the tablets to report technical issues each week. | 2. If yes to previous, could you describe the issue experienced? | Open-ended | - | - | - | - | -
Checkout process is seamless and easy to navigate from a user perspective. | Do guests find the experience better with the tablets? | - less than 5% of customers who use the tablets to report technical issues each week. | 1. Please indicate your position towards the following statement "The Tablets improve my overall experience in the restaurant". | True/False | TRUE | FALSE | UNDECIDED